## 工作表1
Item | Responsibility | Percentage Completed | Best Case (man day) | Most Likely Case (man day) | Worst Case (man day) | Expected Case | Standard Deviation | Variance
Survey music API | Arethura | 100% | 3 | 5 | 7 | 5 | 1.7391 | 3.0246
Survey database API | Cliff | 100% | 2 | 3 | 5 | 3.1667 | 1.3043 | 1.7013
Survey facebook API | Carson | 100% | 0.5 | 1 | 2 | 1.0833 | 0.65217 | 0.42533
Draw UI design | all | 100% | 7 | 9 | 14 | 9.5 | 3.0435 | 9.2628
Design class diagram
Client class diagram | all | 100% | 3 | 4 | 7 | 4.3333 | 1.7391 | 3.0246
Server class diagram | all | 100% | 3 | 4 | 7 | 4.3333 | 1.7391 | 3.0246
Design System architeture
Client architeture | all | 100% | 3 | 4 | 7 | 4.3333 | 1.7391 | 3.0246
Server architeture | all | 100% | 3 | 4 | 7 | 4.3333 | 1.7391 | 3.0246
Design SRS
Funicational Requirement | all | 100% | 3 | 3 | 5 | 3.3333 | 0.86957 | 0.75614
Internal Interface Requirement | all | 100% | 3 | 3 | 5 | 3.3333 | 0.86957 | 0.75614
External Interface Requirement | all | 100% | 3 | 3 | 5 | 3.3333 | 0.86957 | 0.75614
Implemet client
Implement login handler | Carson | 100% | 2 | 3 | 5 | 3.1667 | 1.3043 | 1.7013
Implement invitation handler | Judy | 100% | 3 | 5 | 7 | 5 | 1.7391 | 3.0246
Implement session handler | Uiling | 100% | 3 | 5 | 7 | 5 | 1.7391 | 3.0246 | Total VAR | 51.6541
Implement record handler | Cliff | 100% | 3 | 5 | 7 | 5 | 1.7391 | 3.0246 | Total Expected Effort | 0
Implement instrument play | Arethura | 100% | 3 | 5 | 7 | 5 | 1.7391 | 3.0246 | Percentage Confident | 0.75
Implement server | [8 empty] | Devisor | 2.3
Implement connection controller | Uiling | 100% | 3 | 5 | 7 | 5 | 1.7391 | 3.0246 | Percentage Confident Effort | 8.2651
Implement database controller | Cliff | 100% | 3 | 5 | 7 | 5 | 1.7391 | 3.0246 | Z(0.375) | 1.15
Implement manager | Ken | 100% | 3 | 5 | 7 | 5 | 1.7391 | 3.0246
TOTAL |  | 0% | 0 | 0 | 0 | 0